## Summary
MindMosaic programme tracking
One tab per programme. Live counts are ids returned by getExamBank("practice"), measured 15 Oct 2026.
Nothing reaches a child without a human publication approval, and none has ever been recorded.
Programme | Status | Live now | Awaiting your approval | Drafted, not reviewed | Deadline
NAPLAN Year 3 | LIVE | 322 | 44 | 0 | —
NAPLAN Year 5 | LIVE | 353 | 52 | 0 | —
ICAS Year 3 | LIVE | 592 | 0 | 0 | —
ICAS Year 5 | LIVE — THIN | 281 | 0 | 40 | —
Scholarship Y6 | NOT LIVE | 0 | 0 | 160 | 13 Feb 2027
Writing | NOT LIVE | 0 | 0 | 10 | —
AMC | NOT LIVE | 0 | 0 | 60 | —
Total |  | 1548 | 96 | 270
Held for revision (defects found by the external blind review) |  |  | 2
Human publication approvals ever recorded in this repository |  |  | 0
Two things block publication, neither of them content:
1. The approval CSVs are blank. 96 rows need your decisions.
2. PR #52's publish gate executes JavaScript from candidate data. Must be closed first.

## NAPLAN Year 3
NAPLAN-style practice — Year 3
Serving your Grade 3 child today. 44 more items awaiting your approval.
Status: LIVE
Subject | Live now | Awaiting approval | Drafted | Total potential | Note
Numeracy | 128 | 0 | 0 | 128
Reading | 97 | 25 | 0 | 122 | 1 more held for revision
Language conventions | 96 | 19 | 0 | 115 | 1 more held for revision
Writing | 1 | 0 | 0 | 1 | Effectively empty — one item only
Total | 322 | 44 | 0 | 366
Notes
Both held items are defect fixes: an option naming a 'classroom door' the passage never mentions,
and a spelling item where 'cosey' is an attested variant of the keyed 'cosy'.
Difficulty labels: 10 of the 46 reviewed items were flagged as over-labelled.
Next action | Fill the 44-row Year 3 approval CSV once Codex reissues it.

## NAPLAN Year 5
NAPLAN-style practice — Year 5
Serving your Grade 5 child today. 52 more awaiting approval. Known quality gap — see notes.
Status: LIVE
Subject | Live now | Awaiting approval | Drafted | Total potential | Note
Numeracy | 164 | 0 | 0 | 164
Reading | 106 | 32 | 0 | 138 | All 22 'too easy' flags landed here
Language conventions | 82 | 20 | 0 | 102
Writing | 1 | 0 | 0 | 1 | Effectively empty — one item only
Total | 353 | 52 | 0 | 405
Notes
THE QUALITY GAP: the external blind review flagged 22 items as too easy for Year 5, and all 22
were Year 5. Reading items are mostly direct retrieval, including some labelled challenging.
Fix is new harder items (inference, comparison, evidence evaluation), not reworking these.
A 7-item calibration batch has been commissioned to test the generation recipe.
Next action | Fill the 52-row CSV; separately, run the Year 5 reading calibration batch.

## ICAS Year 3
ICAS-style practice — Year 3
The best-stocked programme in the bank. Nothing in flight.
Status: LIVE
Subject | Live now | Awaiting approval | Drafted | Total potential | Note
Numeracy | 101 | 0 | 0 | 101
Reading | 101 | 0 | 0 | 101
Language conventions | 94 | 0 | 0 | 94
Spelling | 98 | 0 | 0 | 98
Science | 99 | 0 | 0 | 99 | Outside your stated scope
Digital technologies | 98 | 0 | 0 | 98 | Outside your stated scope
Writing | 1 | 0 | 0 | 1 | Effectively empty
Total | 592 | 0 | 0 | 592
Notes
No work in flight and none needed on volume.
Science and digital technologies sit outside the Grade 3/5 scope in your project brief —
they are counted here because a child can be served them today.
Next action | None. Leave alone.

## ICAS Year 5
ICAS-style practice — Year 5
The thinnest live programme. Half the Year 3 equivalent in most subjects.
Status: LIVE — THIN
Subject | Live now | Awaiting approval | Drafted | Total potential | Note
Numeracy | 112 | 0 | 0 | 112
Reading | 51 | 0 | 0 | 51 | Year 3 has 101 — half
Language conventions | 37 | 0 | 0 | 37 | Year 3 has 94
Spelling | 45 | 0 | 0 | 45 | Year 3 has 98
Science | 0 | 0 | 40 | 40 | 40 drafted, never reviewed
Digital technologies | 35 | 0 | 0 | 35
Writing | 1 | 0 | 0 | 1 | Effectively empty
Total | 281 | 0 | 40 | 321
Notes
This is the real volume gap, and it is your Grade 5 child's.
Reading 51, spelling 45, language conventions 37 — each roughly half the Year 3 figure.
40 Year 5 science items are drafted but have never entered review.
Next action | Decide whether ICAS Year 5 depth matters before February. If yes, this is the generation target.

## Scholarship Y6
Scholarship-style practice — Year 6
For the Huntingtower / Edutest exam on Saturday 13 February 2027.
Status: NOT LIVE
Subject | Live now | Awaiting approval | Drafted | Total potential | Note
Verbal reasoning | 0 | 0 | 45 | 45 | One full section paper
Numerical reasoning | 0 | 0 | 40 | 40 | One full section paper
Reading | 0 | 0 | 35 | 35 | 4 original passages
Mathematics | 0 | 0 | 40 | 40 | One full section paper
Written expression | 0 | 0 | 0 | 0 | Uses the Writing feature
Total | 0 | 0 | 160 | 160
Notes
Nothing is live. The catalogue entry is hardcoded status: 'coming_soon' at
src/features/catalogue/catalogue.ts:282 — it is NOT computed from readiness, so someone must
flip it by hand when content is ready.
PR #51 is built and CI-green but ships as its own release AFTER the dev-to-main promotion,
because its migration replaces create_exam_session, the live session function.
Batch 1+2 gives exactly ONE paper per section. No retake depth yet.
Next action | Review the 160 drafts in chunks before mid-December. This is the only deadline-bound programme.

## Writing
Written expression — all years
Cross-cutting view. The 4 live items are counted under their own exam-style programmes, not added again here.
Status: NOT LIVE
Subject | Live now | Awaiting approval | Drafted | Total potential | Note
NAPLAN Year 3 | 0 | 0 | 0 | 0 | 1 live item, counted on the NAPLAN Year 3 tab
NAPLAN Year 5 | 0 | 0 | 0 | 0 | 1 live item, counted on the NAPLAN Year 5 tab
ICAS Year 3 | 0 | 0 | 0 | 0 | 1 live item, counted on the ICAS Year 3 tab
ICAS Year 5 | 0 | 0 | 0 | 0 | 1 live item, counted on the ICAS Year 5 tab
Scholarship Year 6 | 0 | 0 | 10 | 10 | 10 prompts drafted
Total | 0 | 0 | 10 | 10
Notes
The timed-writing feature with parent marking is merged to dev (PR #47) but not promoted.
No AI marking of children's writing, per design.md section 29 — a parent marks against a rubric.
Writing is a SUBJECT inside each exam style, so the selector counts those 4 items there.
This tab shows them at zero to avoid double-counting; the Summary total stays at 1,548.
4 placeholder items across the whole bank is not a usable programme.
Next action | After the promotion: approve the 10 Year 6 prompts.

## AMC
AMC-style practice
60 items drafted, none live. No exam_style rows appear in the served bank.
Status: NOT LIVE
Subject | Live now | Awaiting approval | Drafted | Total potential | Note
Year 3 | 0 | 0 | 30 | 30
Year 5 | 0 | 0 | 30 | 30
Total | 0 | 0 | 60 | 60
Notes
Codex's selector breakdown returns only naplan_style and icas_style rows, so amc_style is
genuinely absent from what a child can be served.
amc_style was missing from the server scoring contract until PR #51 added it.
The AMC answer verifier lives at scripts/verify-roadmap-amc-answers.mts with its own solver
dictionary — one of only two parallel answer records in the repo.
Next action | No action scheduled. Decide whether AMC matters before or after February.

## Sources
Where every number came from
Live counts were produced by running the bank selector, not by reading source files or counting manifests.
Figure | Value | Source
Live bank, all programmes | 1,548 | getExamBank("practice") — selectedCount 1548, distinctSelectedIds 1548. Codex, practice-bank-breakdown.mts, 15 Oct 2026
Live split by year | Y3 914 / Y5 634 | Same script grouped by yearLevel. Reconciles with Claude Code's publishedExamBank 1,548 = questionBank 1,005 + 543 factory-only
Live per subject | see each tab | Grouped by JSON.stringify([yearLevel, examStyle, metadata.subject]) over the selector output
Year 3 approval sheet | 44 (was 46) | 26 reading + 20 spelling, minus 2 held for revision. All yearLevel 3, state staged, reviewer cells blank
Year 5 approval sheet | 52 | 32 reading + 20 spelling, 5 passages each rendered once, reviewer cells blank
Items held for revision | 2 | y3-reading-02-q1 (option names a 'classroom door' absent from the passage); y3-spelling-008 ('cosey' is an attested variant of the keyed 'cosy')
External blind cross-check | 98/98 agree | ChatGPT answered all 98 with keys and explanations withheld; chose the declared key every time; all evidence quotes verified verbatim
Difficulty labels over-stated | 22 | Same cross-check: 22 'should be easier', 0 'should be harder'. Independent of the demoted structural gate, which agreed on direction
Year 5 too easy | 22 of 22 | Every 'too easy' flag in the cross-check was Year 5. Zero Year 3
Scholarship drafts | 160 | 45 verbal + 40 numerical + 35 reading + 40 maths on feat/scholarship-track-core, validated by validate-scholarship-drafts.mts
AMC drafts | 60 | amc-y3-draft.json 30 + amc-y5-draft.json 30 in content/roadmap-drafts/
ICAS Y5 science drafts | 40 | content/roadmap-drafts/icas-y5-science-draft.json
Year 6 writing prompts | 10 | content/writing-drafts/year6-written-expression-draft.json
Publication approvals ever recorded | 0 | content/publication-approvals/*.json has never existed on any branch in the repository's history — checked across all refs
Scholarship catalogue gate | status: "coming_soon" | src/features/catalogue/catalogue.ts:282 — hardcoded, not computed from readiness
Exam date | Sat 13 Feb 2027 | Huntingtower scholarships page, Edutest-administered